Before the

**Federal Communications Commission**

**Washington, D.C. 20554**

|  |  |  |
| --- | --- | --- |
| In re Matter of COMCELL, INC.Request for Extension of Time, or in the alternative, Limited Waiver of Substantial Service Requirements for Local Multipoint Distribution Service Station WPOH449 | **)****)****)****)****)****)****)****)****)** | File No. 0005221656 |

**MEMORANDUM OPINION AND ORDER**

**Adopted: August 1, 2013 Released: August 2, 2013**

By the Deputy Chief, Broadband Division, Wireless Telecommunications Bureau:

# INTRODUCTION

1. In this *Memorandum Opinion and Order*, we deny Comcell, Inc’s (“Comcell”) request for extension of time to demonstrate compliance with the substantial service requirements for its Local Multipoint Distribution Service (“LMDS”) license for Station WPOH449, in the Wichita Falls, Texas Basic Trading Area (BTA). Because we deny Comcell’s request, the license for Station WPOH449 automatically terminated, by operation of Commission rule, as of June 1, 2012.

# BACKGROUND

1. In 1997, the Commission allocated 1,300 megahertz of LMDS spectrum in each basic trading area (“BTA”) across the United States.[[1]](#footnote-2) Specifically, the Commission allocated two LMDS licenses per BTA – an “A Block” and a “B Block” in each.[[2]](#footnote-3) The A Block license is comprised of 1,150 megahertz of total bandwidth, and the B Block license is comprised of 150 megahertz of total bandwidth.[[3]](#footnote-4) The A Block consists of the sub bands 27.50-28.35 GHz (the A1 Band); 29.10-29.25 GHz (the A2 Band); and 31.075-31.225 GHz (the A3 Band).[[4]](#footnote-5) The B Block consists of the sub bands 31.00-31.075 (the B1 Band) and 31.225-31.30 GHz (the B2 Band).[[5]](#footnote-6) The same entity may hold the licenses for both the A and B Blocks of spectrum in an individual BTA, but each license is auctioned and licensed separately.
2. LMDS licensees are regulated under Part 101 of the Commission’s rules, which generally governs terrestrial microwave operations, and may provide any service consistent with the Commission’s rules and the licensee’s regulatory status,[[6]](#footnote-7) subject to a ten-year term from the initial license grant date.[[7]](#footnote-8) At the end of the ten-year period, licensees are required to submit an acceptable showing to the Commission demonstrating that they are providing “substantial service” in each licensed area.[[8]](#footnote-9) Failure by any licensee to meet this requirement will result in forfeiture of the license and the licensee will be ineligible to regain it.[[9]](#footnote-10)
3. The final LMDS band allocation was adopted by the Commission on March 20, 1997.[[10]](#footnote-11) Since allocating the LMDS spectrum, the Commission has thus far held two LMDS auctions: Auction 17 and Auction 23.[[11]](#footnote-12) Auction No. 17, the first LMDS auction, began on February 18, 1998, and closed on March 25, 1998.[[12]](#footnote-13) The license for Station WPOH449 was originally issued to Comcell on June 17, 1998, as a result of Auction No. 17.[[13]](#footnote-14)
4. Comcell was originally required to demonstrate substantial service on June 17, 2008, or 10 years after the initial license grant date.[[14]](#footnote-15) On April 15, 2008, Comcell filed an application for an extension of time to demonstrate substantial service for its LMDS license.[[15]](#footnote-16) On June 13, 2008, the Bureau granted Comcell an extension until June 1, 2012 to construct Station WPOH449, resulting in a nearly four-year construction extension.[[16]](#footnote-17)
5. The application was granted with a comment referring to a 2008 Bureau order where the Bureau granted extensions to other LMDS licensees.[[17]](#footnote-18) In the *LMDS Order*,the Wireless Telecommunications Bureau (the “Bureau”) granted the requests for extension of the construction deadlines filed by a large group of LMDS licensees to extend their deadlines to meet the substantial service requirements to June 1, 2012, resulting in a nearly four year construction extension for each of these licensees.[[18]](#footnote-19) The Bureau found that these LMDS licensees faced factors beyond their control, including difficulties in obtaining viable and affordable equipment, that warranted an extension.[[19]](#footnote-20) In making this finding, the Bureau noted that the licensees seeking relief from the construction deadlines represented a majority of LMDS licensees for whom buildout requirements were approaching, and that they all faced these same basic obstacles to timely construction.[[20]](#footnote-21) Thus, these obstacles were not a product of an individual licensee’s short-sightedness or its unfortunate business decisions; rather, the difficulties in procuring the basic equipment necessary for LMDS operations were widespread, stemming from the state of the market. Based on the record evidence, the Bureau anticipated that various developments in the market – arising in large part from the rollout of new services that could provide opportunities for LMDS operations – would help rectify these difficulties. Thus, the Bureau found that LMDS licensees could potentially use their licenses to provide wireless backhaul services to licensees in the 700 MHz band, the Advanced Wireless Services-1 (“AWS-1”) band, and other bands suitable for mobile broadband service, all of which at that time had recently been auctioned, licensed, or put into use.[[21]](#footnote-22) The Bureau anticipated that these bands would develop robustly, along with other mobile and fixed wireless services, and that resulting opportunities for associated LMDS service (such as wireless backhaul) would help spur production of equipment designed for LMDS use and thus facilitate timely construction by LMDS licensees, under the extended buildout deadline set by the Bureau.[[22]](#footnote-23)
6. On May 16, 2012, Comcell filed an application seeking a further one-year extension of time, until June 1, 2013, to construct Station WPOH449.[[23]](#footnote-24) Comcell states that it has been in contact with equipment dealers and has been told that they cannot provide this equipment at this time because of an influx of new orders.[[24]](#footnote-25)

# DISCUSSION

1. We find that Comcell has not justified a grant of an extension of time of the construction deadline for its LMDS license. And without such extension, Comcell’s LMDS license for Station WPOH449 automatically terminated, by operation of Sections 1.946(c) and 1.955(a)(2) of the Commission’s Rules, as of June 1, 2012.[[25]](#footnote-26) We discuss these findings in detail below.
2. Comcell requests a further one-year extension of time, until June 1, 2013, to demonstrate substantial service.[[26]](#footnote-27) As noted above, this is the second extension that Comcell has requested for constructing Station WPOH449. To be eligible for an extension of time to construct, Comcell must show that its “failure to meet the construction deadline is due to involuntary loss of site or other causes beyond its control.”[[27]](#footnote-28) We conclude that Comcell has not met this threshold.
3. Comcell claims that it has been unable to obtain equipment from vendors because of a backlog of new orders.[[28]](#footnote-29) Comcell does not state, however, when it attempted to order equipment. Under the Commission’s rules, a licensee is presumed to be diligent if it orders equipment in the first ninety days of its license term.[[29]](#footnote-30) While we could imagine circumstances under which Comcell would have acted diligently while ordering equipment at a later time, we lack sufficient information to make such a conclusion. Accordingly, we must deny the Extension Request.
4. Authorizations for LMDS licenses automatically terminate if the licensee fails to meet construction or coverage requirements.[[30]](#footnote-31) In light of our decision to deny Comcell’s request for an extension or waiver of the construction requirements on the ground that grant of such request is not in the public interest, Comcell’s license automatically terminated, by operation of Sections 1.946(c) and 1.955(a)(2) of the Commission’s Rules,[[31]](#footnote-32) as of June 1, 2012.

# CONCLUSION AND ORDERING CLAUSES

1. Comcell has failed to justify an extension of time to meet the substantial service deadline for its LMDS station or to justify a waiver of the June 1, 2012 deadline for establishing substantial service. We therefore deny the Extension Application. Accordingly, Comcell’s license to operate LMDS Station WPOH449 automatically terminated, by operation of Commission rule, as of June 1, 2012.
2. Accordingly, IT IS ORDERED, pursuant to Sections 4(i) and 309of the Communications Act of 1934, as amended, 47 U.S.C. §§ 154(i), 309, and Sections 1.925 and 1.946 of the Commission’s Rules, 47 C.F.R. §§ 1.925, 1.946, that the application for extension of time to demonstrate substantial service (File No. 0005221656) filed by Comcell, Inc. on May 16, 2012IS DENIED.
3. IT IS FURTHER ORDERED that, pursuant to Sections 4(i) and 303(r) of the Communications Act, as amended, 47 U.S.C. §§ 154(i), 303(r), and Section 1.955(a)(2) of the Commission’s Rules, 47 C.F.R. § 1.955(a)(2), that the Universal Licensing System SHALL BE UPDATED to reflect that the license issued to Comcell, Inc. for Local Multipoint Distribution Service Station WPOH449 TERMINATED as of June 1, 2012.
4. These actions are taken under delegated authority pursuant to Sections 0.131 and 0.331 of the Commission’s Rules, 47 C.F.R. §§ 0.131, 0.331.

FEDERAL COMMUNICATIONS COMMISSION

John J. Schauble

Deputy Chief, Broadband Division

Wireless Telecommunications Bureau

1. *See* Rulemaking to Amend Parts 1, 2, 21, and 25 of the Commission’s Rules to Redesignate the 27.5 GHz Frequency Band, to Reallocate the 29.5-30.0 GHz Frequency Band, to Establish Rules and Policies For Local Multipoint Distribution Service and For Fixed Satellite Services, CC Docket No. 92-297, *Second Report and Order, Order on Reconsideration and Fifth Notice of Proposed Rulemaking*, 12 FCC Rcd 12545, 12605 ¶ 136 (1997) (”*Second LMDS Report and Order”*); *see also* Rand McNally Commercial Atlas & Marketing Guide 36-39 (123rd ed. 1992). Rand McNally is the copyright owner of the Major Trading Area (MTA) and BTA Listings, which list the BTAs contained in each MTA and the counties within each BTA, as embodied in Rand McNally’s Trading Area System MTA/BTA Diskette, and geographically represented in the map contained in Rand McNally’s Commercial Atlas & Marketing Guide. The conditional use of Rand McNally copyrighted material by interested persons is authorized under a blanket license agreement dated February 10, 1994 and covers use by LMDS applicants. This agreement requires authorized users of the material to include a legend on reproductions (as specified in the license agreement) indicating Rand McNally ownership. The Commission has allocated the LMDS for operations in a total of 493 BTAs throughout the nation. [↑](#footnote-ref-2)
2. *See Second LMDS Report and Order*, 12 FCC Rcd at 12556 ¶ 12. [↑](#footnote-ref-3)
3. *See id.* [↑](#footnote-ref-4)
4. *See* 47 C.F.R. § 101.1005. [↑](#footnote-ref-5)
5. *See id*. [↑](#footnote-ref-6)
6. *See* 47 C.F.R. § 101.1013(b). [↑](#footnote-ref-7)
7. *See Second LMDS Report and Order,* 12 FCC Rcd at 12657 ¶ 259. Pursuant to 47 C.F.R. § 101.67, LMDS licenses are issued for a period not to exceed ten years, subject to renewal upon demonstration of substantial service. [↑](#footnote-ref-8)
8. *See* 47 C.F.R. § 101.1011(a); *see also Second LMDS Report and Order,* 12 FCC Rcd at 12658 ¶¶ 261-262. [↑](#footnote-ref-9)
9. *See* 47 C.F.R. § 101.1011(a). [↑](#footnote-ref-10)
10. *See Second LMDS Report and Order,* 12 FCC Rcd at 12556 ¶ 13; *see also* Rulemaking to Amend Parts 1, 2, 21, and 25 of the Commission’s Rules, to Redesignate the 27.5 GHz Frequency Band, to Reallocate the 29.5-30.0 GHz Frequency Band, to Establish Rules and Policies For Local Multipoint Distribution Service and For Fixed Satellite Services, CC Docket No. 92-297, *First Report and Order and Fourth Notice of Proposed Rulemaking*, 11 FCC Rcd 19005, 19025 ¶ 45 (1996) (allocating the initial 1 gigahertz of spectrum for LMDS and seeking comment on the allocation of an additional 300 megahertz of spectrum at 31.0-31.3 GHz). [↑](#footnote-ref-11)
11. *See, e.g.*,LMDS Auction Closes, *Public Notice,* 13 FCC Rcd 18217 (1998) (*Auction 17 Closing PN*); Local Multipoint Distribution Service Auction Closes, *Public Notice,* 14 FCC Rcd 8543 (1999) (*Auction 23 Closing PN*). [↑](#footnote-ref-12)
12. *See* FCC Announces Spectrum Auction Schedule for 1998, *Public Notice,* 12 FCC Rcd 19726 (1997); *Auction 17 Closing PN,* 13 FCC Rcd at 18217. [↑](#footnote-ref-13)
13. *See* File No. 0000000025 (granted June 17, 1998); *see also* FCC Announces the Conditional Grant of 199 Local Multipoint Distribution Service Licenses, *Public Notice*, 13 FCC Rcd 16730 (WTB 1998). [↑](#footnote-ref-14)
14. *See Second LMDS Report and Order,* 12 FCC Rcd at 12657 ¶ 259. [↑](#footnote-ref-15)
15. File No. 0003397333 (filed Apr. 15, 2008). [↑](#footnote-ref-16)
16. File No. 0003397333 (granted June 13, 2008). [↑](#footnote-ref-17)
17. *Id.*, *citing* Applications filed by Licensees in the Local Multipoint Distribution Service (LMDS) Seeking Waivers of Section 101.1011 of the Commission’s Rules and Extensions of Time to Construct and Demonstrate Substantial Service, *Memorandum Opinion and Order*, 23 FCC Rcd 5894 (WTB 2008) (*LMDS Order*). [↑](#footnote-ref-18)
18. *LMDS Order*. [↑](#footnote-ref-19)
19. *Id.* at 5905 ¶ 24. [↑](#footnote-ref-20)
20. *Id*. [↑](#footnote-ref-21)
21. *Id.* at 5905 ¶ 25. [↑](#footnote-ref-22)
22. *Id*. [↑](#footnote-ref-23)
23. *See* File No. 0005221656 (filed May 16, 2012) (Extension Application). [↑](#footnote-ref-24)
24. Extension Application, Request for Extension. [↑](#footnote-ref-25)
25. 47 C.F.R. §§ 1.946(c) (providing that if a licensee in the Wireless Radio Services fails to commence service or operations by the expiration of its construction period or to meet its coverage or substantial service obligations by the expiration of its coverage period, its authorization terminates automatically, without specific Commission action, on the date the construction or coverage period expires) and 1.955(a)(2) (cross-referencing Section 1.946(c) and reiterating that authorizations in the Wireless Radio Services automatically terminate without specific Commission action, if the licensee fails to meet applicable construction or coverage requirements). [↑](#footnote-ref-26)
26. Extension Application. [↑](#footnote-ref-27)
27. 47 C.F.R. § 1.946(e)(1). [↑](#footnote-ref-28)
28. Extension Application, Request for Extension. [↑](#footnote-ref-29)
29. *See* 47 C.F.R. § 1.946(e)(2). [↑](#footnote-ref-30)
30. 47 C.F.R. §§ 1.946(c) and 1.955(a)(2). [↑](#footnote-ref-31)
31. *Id*. [↑](#footnote-ref-32)