**DA 14-620**

Southern California Edison Company

2131 Walnut Grove

Rosemead, CA 91770

ATTN: Mr. Raul Perez

RE: Letter Dated May 7, 2014 – Request for Extension of Time

Dear Mr. Perez:

 This letter is in response to your May 7, 2014 request for an extension of time, until July 10, 2014, to submit a cost estimate for the reconfiguration of the Southern California Edison Company (SCEC) 800 MHz communications system. For the reasons set out below, your extension request is denied. SCEC must submit its cost estimate to Sprint Corporation (Sprint) and the 800 MHz Transition Administrator no later than June 16, 2014.

 This is the third request SCEC has filed for an extension of time within which to file its cost estimate. SCEC represents that its vendor, Motorola Solutions, will provide a statement of work by May 30, 2014 and requests until July 10, 2014 to perform a “thorough review of the costing estimate to validate the Motorola’s deliverable.”

 SCEC has not detailed what constitutes its “thorough review” much less justified why the review should take forty-one days. It claims, however, that the additional time is warranted because changes to the statement of work may be necessary. We are not persuaded that, with diligence, SCEC and Motorola Solutions cannot complete their work by June 16, 2014, thereby allowing 18 days for analysis of the statement of work and the implementation of any changes. Therefore, we are denying SCEC’s third extension request.

 Accordingly, IT IS ORDERED, that the May 7, 2014 request for extension of time filed by the Southern California Edison Company IS DENIED.

IT IS FURTHER ORDERED that Southern California Edison Company shall submit a cost estimate to Sprint Corporation and the 800 MHz Transition Administrator no later than June 16, 2014.

We take this action pursuant to delegated authority under Sections 0.191 and 0.392 of the Commission's rules, 47 C.F.R. §§ 0.191, 0.392.

FEDERAL COMMUNICATIONS COMMISSION

Michael J. Wilhelm

Deputy Chief, Policy and Licensing Division

Public Safety and Homeland Security Bureau