DA 16-1273

November 10, 2016

**WIRELESS TELECOMMUNICATIONS BUREAU SEEKS COMMENT ON HELEN WONG-ARMIJO, FCR, INC., SKYBRIDGE SPECTRUM FOUNDATION, AND TELESAURUS HOLDINGS GB LLC, REQUESTS FOR MULTILATERATION LOCATION AND MONITORING SERVICE WAIVER AND CONSTRUCTION EXTENSIONS**

 **WT Docket No. 16-385**

**Comments Due: November 30, 2016**

**Reply Comments Due: December 12, 2016**

On August 29, 2016, Helen Wong-Armijo (Wong-Armijo) filed applications requesting an extension of its midterm construction deadline, and on September 12, 2016, filed applications requesting an extension of its final construction deadline for eighty-four of its Channel Block B and C Multilateration Location and Monitoring Service (M-LMS) licenses.[[1]](#footnote-1) Specifically, Wong-Armijo seeks to extend both the midterm and final construction deadlines to October 5, 2021, the expiration date of the licenses. In the alternative, the Wong-Armijo Extension and Waiver Requests seek a waiver of Section 90.155(d) of the Commission’s rules for license buildout requirements.[[2]](#footnote-2)

On August 31, 2016, FCR, Inc. (FCR), filed applications seeking a waiver of Section 90.155(d) of the Commission’s rules for license buildout requirements with respect to its midterm construction deadline, and on September 12, 2016, filed applications seeking waiver of Section 90.155(d) with respect to its final construction deadline for thirteen of its Channel Block A M-LMS licenses.[[3]](#footnote-3) In the alternative, the FCR Extension and Waiver Requests seek an extension of its construction deadlines.[[4]](#footnote-4) Similar to Wong-Armijo’s request, FCR seeks to extend both the midterm and final construction deadlines to the respective expiration dates of its thirteen licenses.[[5]](#footnote-5)

On September 2, 2016, Skybridge Spectrum Foundation (Skybridge) and Telesaurus Holdings GB LLC (Telesaurus), acting through a court-appointed receiver,[[6]](#footnote-6) jointly filed applications for extension of the construction deadlines for Skybridge’s 128 Channel Block A M-LMS licenses and one Telesaurus Channel Block C M-LMS license.[[7]](#footnote-7) The Receiver requested an extension of the first construction deadline until September 4, 2018.[[8]](#footnote-8) The Receiver also seeks, in the alternative, an extended timeframe for construction, if that relief is granted to PCS Partners, L.P. in response to its separate request for extension and waiver filed on April 15, 2016.[[9]](#footnote-9)

By this Public Notice, we seek comment on the Extension and Waiver Requests, particularly with respect to any public interest benefit and potential impact on operations within the 902-928 MHz band and in adjacent bands.

**Procedural Matters**

Pursuant to Sections 1.415 and 1.419 of the Commission’s rules, 47 CFR §§ 1.415, 1.419, interested parties may file comments and reply comments on or before the dates indicated on the first page of this document. Comments may be filed using the Commission’s Electronic Comment Filing System (“ECFS”). *See Electronic Filing of Documents in Rulemaking Proceedings*, 63 FR 24121 (1998).

* Electronic Filers: Comments may be filed electronically using the Internet by accessing the ECFS: <http://fjallfoss.fcc.gov/ecfs2/>.
* Paper Filers: Parties who choose to file by paper must file an original and one copy of each filing. If more than one docket or rulemaking number appears in the caption of this proceeding, filers must submit two additional copies for each additional docket or rulemaking number.

Filings can be sent by hand or messenger delivery, by commercial overnight courier, or by first-class or overnight U.S. Postal Service mail. All filings must be addressed to the Commission’s Secretary, Office of the Secretary, Federal Communications Commission.

* All hand-delivered or messenger-delivered paper filings for the Commission’s Secretary must be delivered to FCC Headquarters at 445 12th St., SW, Room TW-A325, Washington, DC 20554. The filing hours are 8:00 a.m. to 7:00 p.m. All hand deliveries must be held together with rubber bands or fasteners. Any envelopes and boxes must be disposed of before entering the building.
* Commercial overnight mail (other than U.S. Postal Service Express Mail and Priority Mail) must be sent to 9300 East Hampton Drive, Capitol Heights, MD 20743.
* U.S. Postal Service first-class, Express, and Priority mail must be addressed to 445 12th Street, SW, Washington DC 20554.

People with Disabilities: To request materials in accessible formats for people with disabilities (braille, large print, electronic files, audio format), send an e-mail to fcc504@fcc.gov or call the Consumer & Governmental Affairs Bureau at 202-418-0530 (voice), 202-418-0432 (tty).

This proceeding has been designated as a “permit-but-disclose” proceeding in accordance with the Commission's *ex parte* rules.[[10]](#footnote-10) Persons making *ex parte* presentations must file a copy of any written presentation or a memorandum summarizing any oral presentation within two business days after the presentation (unless a different deadline applicable to the Sunshine period applies). Persons making oral *ex parte* presentations are reminded that memoranda summarizing the presentation must (1) list all persons attending or otherwise participating in the meeting at which the *ex parte* presentation was made, and (2) summarize all data presented and arguments made during the presentation. If the presentation consisted in whole or in part of the presentation of data or arguments already reflected in the presenter’s written comments, memoranda or other filings in the proceeding, the presenter may provide citations to such data or arguments in his or her prior comments, memoranda, or other filings (specifying the relevant page and/or paragraph numbers where such data or arguments can be found) in lieu of summarizing them in the memorandum. Documents shown or given to Commission staff during *ex parte* meetings are deemed to be written *ex parte* presentations and must be filed consistent with rule 1.1206(b).

In proceedings governed by rule 1.49(f) or for which the Commission has made available a method of electronic filing, written *ex parte* presentations and memoranda summarizing oral *ex parte* presentations, and all attachments thereto, must be filed through the electronic comment filing system available for that proceeding, and must be filed in their native format (e.g., .doc, .xml, .ppt, searchable .pdf). Participants in this proceeding should familiarize themselves with the Commission’s *ex parte* rules.

For further information, contact Ms. Anna Gentry of the Mobility Division, Wireless Telecommunications Bureau, at (202) 418-7769 or via e-mail at anna.gentry@fcc.gov.

Action by the Chief, Mobility Division, Wireless Telecommunications Bureau.

- FCC -

**APPENDIX A**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **File Number** | **Call Sign** | **Purpose** | **Receipt Date** | **Radio Service Code** | **Channel Block** | **Market Name** |
| 0007435092 | WPTH955 | Extension of First Deadline | 8/29/2016 | LS | C  | Salisbury, MD-DE-VA |
| 0007450628 | WPTH955 | Extension of Second Deadline | 9/12/2016 | LS | C  | Salisbury, MD-DE-VA |
| 0007435093 | WPTH956 | Extension of First Deadline | 8/29/2016 | LS | C  | Staunton, VA-WV |
| 0007450629 | WPTH956 | Extension of Second Deadline | 9/12/2016 | LS | C  | Staunton, VA-WV |
| 0007435094 | WPTH957 | Extension of First Deadline | 8/29/2016 | LS | B  | Fayetteville, NC |
| 0007450630 | WPTH957 | Extension of Second Deadline | 9/12/2016 | LS | B  | Fayetteville, NC |
| 0007435095 | WPTH958 | Extension of First Deadline | 8/29/2016 | LS | C  | Fayetteville, NC |
| 0007450631 | WPTH958 | Extension of Second Deadline | 9/12/2016 | LS | C  | Fayetteville, NC |
| 0007435096 | WPTH959 | Extension of First Deadline | 8/29/2016 | LS | B  | Dothan, AL-FL-GA |
| 0007450632 | WPTH959 | Extension of Second Deadline | 9/12/2016 | LS | B  | Dothan, AL-FL-GA |
| 0007435097 | WPTH960 | Extension of First Deadline | 8/29/2016 | LS | C  | Dothan, AL-FL-GA |
| 0007450633 | WPTH960 | Extension of Second Deadline | 9/12/2016 | LS | C  | Dothan, AL-FL-GA |
| 0007435098 | WPTH961 | Extension of First Deadline | 8/29/2016 | LS | B  | Albany, GA |
| 0007450634 | WPTH961 | Extension of Second Deadline | 9/12/2016 | LS | B  | Albany, GA |
| 0007435099 | WPTH962 | Extension of First Deadline | 8/29/2016 | LS | C  | Albany, GA |
| 0007450635 | WPTH962 | Extension of Second Deadline | 9/12/2016 | LS | C  | Albany, GA |
| 0007435100 | WPTH963 | Extension of First Deadline | 8/29/2016 | LS | B  | Columbus, GA-AL |
| 0007450636 | WPTH963 | Extension of Second Deadline | 9/12/2016 | LS | B  | Columbus, GA-AL |
| 0007435101 | WPTH964 | Extension of First Deadline | 8/29/2016 | LS | C  | Columbus, GA-AL |
| 0007450637 | WPTH964 | Extension of Second Deadline | 9/12/2016 | LS | C  | Columbus, GA-AL |
| 0007435102 | WPTH965 | Extension of First Deadline | 8/29/2016 | LS | B  | Asheville, NC |
| 0007450638 | WPTH965 | Extension of Second Deadline | 9/12/2016 | LS | B  | Asheville, NC |
| 0007435103 | WPTH966 | Extension of First Deadline | 8/29/2016 | LS | C  | Asheville, NC |
| 0007450639 | WPTH966 | Extension of Second Deadline | 9/12/2016 | LS | C  | Asheville, NC |
| 0007435104 | WPTH967 | Extension of First Deadline | 8/29/2016 | LS | B  | Hickory-Morganton, NC-TN |
| 0007450640 | WPTH967 | Extension of Second Deadline | 9/12/2016 | LS | B  | Hickory-Morganton, NC-TN |
| 0007435105 | WPTH968 | Extension of First Deadline | 8/29/2016 | LS | C  | Hickory-Morganton, NC-TN |
| 0007450641 | WPTH968 | Extension of Second Deadline | 9/12/2016 | LS | C  | Hickory-Morganton, NC-TN |
| 0007435106 | WPTH969 | Extension of First Deadline | 8/29/2016 | LS | B  | Wheeling, WV-OH |
| 0007450642 | WPTH969 | Extension of Second Deadline | 9/12/2016 | LS | B  | Wheeling, WV-OH |
| 0007435107 | WPTH970 | Extension of First Deadline | 8/29/2016 | LS | C  | Wheeling, WV-OH |
| 0007450643 | WPTH970 | Extension of Second Deadline | 9/12/2016 | LS | C  | Wheeling, WV-OH |
| 0007435108 | WPTH971 | Extension of First Deadline | 8/29/2016 | LS | C  | Northern Michigan, MI |
| 0007450644 | WPTH971 | Extension of Second Deadline | 9/12/2016 | LS | C  | Northern Michigan, MI |
| 0007435109 | WPTH972 | Extension of First Deadline | 8/29/2016 | LS | B  | Appleton-Oshkosh-Neenah, WI |
| 0007450645 | WPTH972 | Extension of Second Deadline | 9/12/2016 | LS | B  | Appleton-Oshkosh-Neenah, WI |
| 0007435110 | WPTH973 | Extension of First Deadline | 8/29/2016 | LS | C  | Appleton-Oshkosh-Neenah, WI |
| 0007450646 | WPTH973 | Extension of Second Deadline | 9/12/2016 | LS | C  | Appleton-Oshkosh-Neenah, WI |
| 0007435111 | WPTH974 | Extension of First Deadline | 8/29/2016 | LS | C  | Traverse City, MI |
| 0007450647 | WPTH974 | Extension of Second Deadline | 9/12/2016 | LS | C  | Traverse City, MI |
| 0007435112 | WPTH975 | Extension of First Deadline | 8/29/2016 | LS | C  | Paducah, KY-IL |
| 0007450648 | WPTH975 | Extension of Second Deadline | 9/12/2016 | LS | C  | Paducah, KY-IL |
| 0007435113 | WPTH976 | Extension of First Deadline | 8/29/2016 | LS | C  | Greenville, MS |
| 0007450649 | WPTH976 | Extension of Second Deadline | 9/12/2016 | LS | C  | Greenville, MS |
| 0007435114 | WPTH977 | Extension of First Deadline | 8/29/2016 | LS | B  | Montgomery, AL |
| 0007450650 | WPTH977 | Extension of Second Deadline | 9/12/2016 | LS | B  | Montgomery, AL |
| 0007435115 | WPTH978 | Extension of First Deadline | 8/29/2016 | LS | C  | Montgomery, AL |
| 0007450651 | WPTH978 | Extension of Second Deadline | 9/12/2016 | LS | C  | Montgomery, AL |
| 0007435116 | WPTH979 | Extension of First Deadline | 8/29/2016 | LS | B  | Biloxi-Gulfport-Pascagoula, MS |
| 0007450652 | WPTH979 | Extension of Second Deadline | 9/12/2016 | LS | B  | Biloxi-Gulfport-Pascagoula, MS |
| 0007435117 | WPTH980 | Extension of First Deadline | 8/29/2016 | LS | C  | Biloxi-Gulfport-Pascagoula, MS |
| 0007450653 | WPTH980 | Extension of Second Deadline | 9/12/2016 | LS | C  | Biloxi-Gulfport-Pascagoula, MS |
| 0007435118 | WPTH981 | Extension of First Deadline | 8/29/2016 | LS | B  | Beaumont-Port Arthur, TX |
| 0007450654 | WPTH981 | Extension of Second Deadline | 9/12/2016 | LS | B  | Beaumont-Port Arthur, TX |
| 0007435119 | WPTH982 | Extension of First Deadline | 8/29/2016 | LS | C  | Beaumont-Port Arthur, TX |
| 0007450655 | WPTH982 | Extension of Second Deadline | 9/12/2016 | LS | C  | Beaumont-Port Arthur, TX |
| 0007435120 | WPTH983 | Extension of First Deadline | 8/29/2016 | LS | B  | Monroe, LA |
| 0007450656 | WPTH983 | Extension of Second Deadline | 9/12/2016 | LS | B  | Monroe, LA |
| 0007435121 | WPTH984 | Extension of First Deadline | 8/29/2016 | LS | C  | Monroe, LA |
| 0007450657 | WPTH984 | Extension of Second Deadline | 9/12/2016 | LS | C  | Monroe, LA |
| 0007435122 | WPTH985 | Extension of First Deadline | 8/29/2016 | LS | C  | Fort Smith, AR-OK |
| 0007450658 | WPTH985 | Extension of Second Deadline | 9/12/2016 | LS | C  | Fort Smith, AR-OK |
| 0007435123 | WPTH986 | Extension of First Deadline | 8/29/2016 | LS | C  | Fayetteville-Springdale-Rogers |
| 0007450659 | WPTH986 | Extension of Second Deadline | 9/12/2016 | LS | C  | Fayetteville-Springdale-Rogers |
| 0007435124 | WPTH987 | Extension of First Deadline | 8/29/2016 | LS | C  | Joplin, MO-KS-OK |
| 0007450660 | WPTH987 | Extension of Second Deadline | 9/12/2016 | LS | C  | Joplin, MO-KS-OK |
| 0007435125 | WPTH988 | Extension of First Deadline | 8/29/2016 | LS | C  | Jonesboro, AR-MO |
| 0007450661 | WPTH988 | Extension of Second Deadline | 9/12/2016 | LS | C  | Jonesboro, AR-MO |
| 0007435126 | WPTH989 | Extension of First Deadline | 8/29/2016 | LS | B  | Springfield, IL-MO |
| 0007450662 | WPTH989 | Extension of Second Deadline | 9/12/2016 | LS | B  | Springfield, IL-MO |
| 0007435127 | WPTH990 | Extension of First Deadline | 8/29/2016 | LS | C  | Springfield, IL-MO |
| 0007450663 | WPTH990 | Extension of Second Deadline | 9/12/2016 | LS | C  | Springfield, IL-MO |
| 0007435128 | WPTH991 | Extension of First Deadline | 8/29/2016 | LS | C  | Columbia, MO |
| 0007450664 | WPTH991 | Extension of Second Deadline | 9/12/2016 | LS | C  | Columbia, MO |
| 0007435129 | WPTH992 | Extension of First Deadline | 8/29/2016 | LS | C  | Cedar Rapids, IA |
| 0007450665 | WPTH992 | Extension of Second Deadline | 9/12/2016 | LS | C  | Cedar Rapids, IA |
| 0007435130 | WPTH993 | Extension of First Deadline | 8/29/2016 | LS | C  | La Crosse, WI-MN |
| 0007450666 | WPTH993 | Extension of Second Deadline | 9/12/2016 | LS | C  | La Crosse, WI-MN |
| 0007435131 | WPTH994 | Extension of First Deadline | 8/29/2016 | LS | C  | Rochester, MN-IA-WI |
| 0007450667 | WPTH994 | Extension of Second Deadline | 9/12/2016 | LS | C  | Rochester, MN-IA-WI |
| 0007435132 | WPTH995 | Extension of First Deadline | 8/29/2016 | LS | B  | Wausau, WI |
| 0007450668 | WPTH995 | Extension of Second Deadline | 9/12/2016 | LS | B  | Wausau, WI |
| 0007435133 | WPTH996 | Extension of First Deadline | 8/29/2016 | LS | C  | Wausau, WI |
| 0007450669 | WPTH996 | Extension of Second Deadline | 9/12/2016 | LS | C  | Wausau, WI |
| 0007435134 | WPTH997 | Extension of First Deadline | 8/29/2016 | LS | B  | Duluth-Superior, MN-WI |
| 0007450670 | WPTH997 | Extension of Second Deadline | 9/12/2016 | LS | B  | Duluth-Superior, MN-WI |
| 0007435135 | WPTH998 | Extension of First Deadline | 8/29/2016 | LS | C  | Duluth-Superior, MN-WI |
| 0007450671 | WPTH998 | Extension of Second Deadline | 9/12/2016 | LS | C  | Duluth-Superior, MN-WI |
| 0007435136 | WPTH999 | Extension of First Deadline | 8/29/2016 | LS | C  | Grand Forks, ND-MN |
| 0007450672 | WPTH999 | Extension of Second Deadline | 9/12/2016 | LS | C  | Grand Forks, ND-MN |
| 0007435137 | WPTI200 | Extension of First Deadline | 8/29/2016 | LS | C  | Minot, ND |
| 0007450673 | WPTI200 | Extension of Second Deadline | 9/12/2016 | LS | C  | Minot, ND |
| 0007435138 | WPTI201 | Extension of First Deadline | 8/29/2016 | LS | C  | Bismarck, ND-MT-SD |
| 0007450674 | WPTI201 | Extension of Second Deadline | 9/12/2016 | LS | C  | Bismarck, ND-MT-SD |
| 0007435139 | WPTI202 | Extension of First Deadline | 8/29/2016 | LS | C  | Fargo-Moorhead, ND-MN |
| 0007450675 | WPTI202 | Extension of Second Deadline | 9/12/2016 | LS | C  | Fargo-Moorhead, ND-MN |
| 0007435140 | WPTI203 | Extension of First Deadline | 8/29/2016 | LS | C  | Aberdeen, SD |
| 0007450676 | WPTI203 | Extension of Second Deadline | 9/12/2016 | LS | C  | Aberdeen, SD |
| 0007435141 | WPTI204 | Extension of First Deadline | 8/29/2016 | LS | C  | Rapid City, SD-MT-ND-NE |
| 0007450677 | WPTI204 | Extension of Second Deadline | 9/12/2016 | LS | C  | Rapid City, SD-MT-ND-NE |
| 0007435142 | WPTI205 | Extension of First Deadline | 8/29/2016 | LS | C  | Sioux City, IA-NE-SD |
| 0007450678 | WPTI205 | Extension of Second Deadline | 9/12/2016 | LS | C  | Sioux City, IA-NE-SD |
| 0007435143 | WPTI206 | Extension of First Deadline | 8/29/2016 | LS | B  | Lincoln, NE |
| 0007450679 | WPTI206 | Extension of Second Deadline | 9/12/2016 | LS | B  | Lincoln, NE |
| 0007435144 | WPTI207 | Extension of First Deadline | 8/29/2016 | LS | C  | Lincoln, NE |
| 0007450680 | WPTI207 | Extension of Second Deadline | 9/12/2016 | LS | C  | Lincoln, NE |
| 0007435145 | WPTI208 | Extension of First Deadline | 8/29/2016 | LS | C  | Grand Island, NE |
| 0007450681 | WPTI208 | Extension of Second Deadline | 9/12/2016 | LS | C  | Grand Island, NE |
| 0007435146 | WPTI209 | Extension of First Deadline | 8/29/2016 | LS | C  | North Platte, NE-CO |
| 0007450682 | WPTI209 | Extension of Second Deadline | 9/12/2016 | LS | C  | North Platte, NE-CO |
| 0007435147 | WPTI210 | Extension of First Deadline | 8/29/2016 | LS | B  | Topeka, KS |
| 0007450683 | WPTI210 | Extension of Second Deadline | 9/12/2016 | LS | B  | Topeka, KS |
| 0007435148 | WPTI211 | Extension of First Deadline | 8/29/2016 | LS | C  | Topeka, KS |
| 0007450684 | WPTI211 | Extension of Second Deadline | 9/12/2016 | LS | C  | Topeka, KS |
| 0007435149 | WPTI212 | Extension of First Deadline | 8/29/2016 | LS | C  | Western Oklahoma, OK |
| 0007450685 | WPTI212 | Extension of Second Deadline | 9/12/2016 | LS | C  | Western Oklahoma, OK |
| 0007435150 | WPTI213 | Extension of First Deadline | 8/29/2016 | LS | C  | Abilene, TX |
| 0007450686 | WPTI213 | Extension of Second Deadline | 9/12/2016 | LS | C  | Abilene, TX |
| 0007435151 | WPTI214 | Extension of First Deadline | 8/29/2016 | LS | C  | San Angelo, TX |
| 0007450687 | WPTI214 | Extension of Second Deadline | 9/12/2016 | LS | C  | San Angelo, TX |
| 0007435152 | WPTI215 | Extension of First Deadline | 8/29/2016 | LS | B  | Odessa-Midland, TX |
| 0007450688 | WPTI215 | Extension of Second Deadline | 9/12/2016 | LS | B  | Odessa-Midland, TX |
| 0007435153 | WPTI216 | Extension of First Deadline | 8/29/2016 | LS | C  | Odessa-Midland, TX |
| 0007450689 | WPTI216 | Extension of Second Deadline | 9/12/2016 | LS | C  | Odessa-Midland, TX |
| 0007435154 | WPTI217 | Extension of First Deadline | 8/29/2016 | LS | C  | Hobbs, NM-TX |
| 0007450690 | WPTI217 | Extension of Second Deadline | 9/12/2016 | LS | C  | Hobbs, NM-TX |
| 0007435155 | WPTI218 | Extension of First Deadline | 8/29/2016 | LS | B  | Lubbock, TX |
| 0007450691 | WPTI218 | Extension of Second Deadline | 9/12/2016 | LS | B  | Lubbock, TX |
| 0007435156 | WPTI219 | Extension of First Deadline | 8/29/2016 | LS | C  | Lubbock, TX |
| 0007450692 | WPTI219 | Extension of Second Deadline | 9/12/2016 | LS | C  | Lubbock, TX |
| 0007435157 | WPTI220 | Extension of First Deadline | 8/29/2016 | LS | B  | Amarillo, TX-NM |
| 0007450693 | WPTI220 | Extension of Second Deadline | 9/12/2016 | LS | B  | Amarillo, TX-NM |
| 0007435158 | WPTI221 | Extension of First Deadline | 8/29/2016 | LS | C  | Amarillo, TX-NM |
| 0007450694 | WPTI221 | Extension of Second Deadline | 9/12/2016 | LS | C  | Amarillo, TX-NM |
| 0007435159 | WPTI222 | Extension of First Deadline | 8/29/2016 | LS | C  | Santa Fe, NM |
| 0007450695 | WPTI222 | Extension of Second Deadline | 9/12/2016 | LS | C  | Santa Fe, NM |
| 0007435160 | WPTI223 | Extension of First Deadline | 8/29/2016 | LS | C  | Pueblo, CO-NM |
| 0007450696 | WPTI223 | Extension of Second Deadline | 9/12/2016 | LS | C  | Pueblo, CO-NM |
| 0007435161 | WPTI224 | Extension of First Deadline | 8/29/2016 | LS | C  | Scottsbluff, NE-WY |
| 0007450697 | WPTI224 | Extension of Second Deadline | 9/12/2016 | LS | C  | Scottsbluff, NE-WY |
| 0007435162 | WPTI225 | Extension of First Deadline | 8/29/2016 | LS | B  | Casper, WY-ID-UT |
| 0007450698 | WPTI225 | Extension of Second Deadline | 9/12/2016 | LS | B  | Casper, WY-ID-UT |
| 0007435163 | WPTI226 | Extension of First Deadline | 8/29/2016 | LS | C  | Casper, WY-ID-UT |
| 0007450699 | WPTI226 | Extension of Second Deadline | 9/12/2016 | LS | C  | Casper, WY-ID-UT |
| 0007435164 | WPTI227 | Extension of First Deadline | 8/29/2016 | LS | B  | Billings, MT-WY |
| 0007450700 | WPTI227 | Extension of Second Deadline | 9/12/2016 | LS | B  | Billings, MT-WY |
| 0007435165 | WPTI228 | Extension of First Deadline | 8/29/2016 | LS | C  | Billings, MT-WY |
| 0007450701 | WPTI228 | Extension of Second Deadline | 9/12/2016 | LS | C  | Billings, MT-WY |
| 0007435166 | WPTI229 | Extension of First Deadline | 8/29/2016 | LS | C  | Great Falls, MT |
| 0007450702 | WPTI229 | Extension of Second Deadline | 9/12/2016 | LS | C  | Great Falls, MT |
| 0007435167 | WPTI230 | Extension of First Deadline | 8/29/2016 | LS | C  | Missoula, MT |
| 0007450703 | WPTI230 | Extension of Second Deadline | 9/12/2016 | LS | C  | Missoula, MT |
| 0007435168 | WPTI231 | Extension of First Deadline | 8/29/2016 | LS | C  | Idaho Falls, ID-WY |
| 0007450704 | WPTI231 | Extension of Second Deadline | 9/12/2016 | LS | C  | Idaho Falls, ID-WY |
| 0007435169 | WPTI232 | Extension of First Deadline | 8/29/2016 | LS | C  | Twin Falls, ID |
| 0007450705 | WPTI232 | Extension of Second Deadline | 9/12/2016 | LS | C  | Twin Falls, ID |
| 0007435170 | WPTI233 | Extension of First Deadline | 8/29/2016 | LS | B  | Flagstaff, AZ-UT |
| 0007450706 | WPTI233 | Extension of Second Deadline | 9/12/2016 | LS | B  | Flagstaff, AZ-UT |
| 0007435171 | WPTI234 | Extension of First Deadline | 8/29/2016 | LS | C  | Flagstaff, AZ-UT |
| 0007450707 | WPTI234 | Extension of Second Deadline | 9/12/2016 | LS | C  | Flagstaff, AZ-UT |
| 0007435172 | WPTI235 | Extension of First Deadline | 8/29/2016 | LS | C  | Farmington, NM-CO |
| 0007450708 | WPTI235 | Extension of Second Deadline | 9/12/2016 | LS | C  | Farmington, NM-CO |
| 0007435173 | WPTI236 | Extension of First Deadline | 8/29/2016 | LS | B  | Redding, CA-OR |
| 0007450709 | WPTI236 | Extension of Second Deadline | 9/12/2016 | LS | B  | Redding, CA-OR |
| 0007435174 | WPTI237 | Extension of First Deadline | 8/29/2016 | LS | C  | Redding, CA-OR |
| 0007450710 | WPTI237 | Extension of Second Deadline | 9/12/2016 | LS | C  | Redding, CA-OR |
| 0007435175 | WPTI238 | Extension of First Deadline | 8/29/2016 | LS | C  | Pendleton, OR-WA |
| 0007450711 | WPTI238 | Extension of Second Deadline | 9/12/2016 | LS | C  | Pendleton, OR-WA |

**APPENDIX B**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **File Number** | **Call Sign** | **Purpose** | **Receipt Date** | **Radio Service Code** | **Channel Block** | **Market Name** |
| 0007438931 | WPOJ871 | Extension of First Deadline | 8/31/2016 | LS | A | Buffalo-Niagara Falls, NY-PA |
| 0007450762 | WPOJ871 | Extension of Second Deadline | 9/12/2016 | LS | A | Buffalo-Niagara Falls, NY-PA |
| 0007438932 | WPOJ872 | Extension of First Deadline | 8/31/2016 | LS | A | Tampa-St. Petersburg-Clearwate |
| 0007450763 | WPOJ872 | Extension of Second Deadline | 9/12/2016 | LS | A | Tampa-St. Petersburg-Clearwate |
| 0007438933 | WPOJ873 | Extension of First Deadline | 8/31/2016 | LS | A | Atlanta, GA-AL-NC |
| 0007450764 | WPOJ873 | Extension of Second Deadline | 9/12/2016 | LS | A | Atlanta, GA-AL-NC |
| 0007438934 | WPOJ874 | Extension of First Deadline | 8/31/2016 | LS | A | Cleveland-Akron, OH-PA |
| 0007450765 | WPOJ874 | Extension of Second Deadline | 9/12/2016 | LS | A | Cleveland-Akron, OH-PA |
| 0007438935 | WPOJ875 | Extension of First Deadline | 8/31/2016 | LS | A | Las Vegas, NV-AZ-UT |
| 0007450766 | WPOJ875 | Extension of Second Deadline | 9/12/2016 | LS | A | Las Vegas, NV-AZ-UT |
| 0007438976 | WPTH901 | Extension of First Deadline | 8/31/2016 | LS | A | Bangor, ME |
| 0007450792 | WPTH901 | Extension of Second Deadline | 9/12/2016 | LS | A | Bangor, ME |
| 0007438977 | WPTH902 | Extension of First Deadline | 8/31/2016 | LS | A | Portland, ME |
| 0007450793 | WPTH902 | Extension of Second Deadline | 9/12/2016 | LS | A | Portland, ME |
| 0007438978 | WPTH903 | Extension of First Deadline | 8/31/2016 | LS | A | Johnson City-Kingsport-Bristol |
| 0007450794 | WPTH903 | Extension of Second Deadline | 9/12/2016 | LS | A | Johnson City-Kingsport-Bristol |
| 0007438979 | WPTH904 | Extension of First Deadline | 8/31/2016 | LS | A | Charleston, WV-KY-OH |
| 0007450795 | WPTH904 | Extension of Second Deadline | 9/12/2016 | LS | A | Charleston, WV-KY-OH |
| 0007438980 | WPTH905 | Extension of First Deadline | 8/31/2016 | LS | A | Wheeling, WV-OH |
| 0007450796 | WPTH905 | Extension of Second Deadline | 9/12/2016 | LS | A | Wheeling, WV-OH |
| 0007438981 | WPTH906 | Extension of First Deadline | 8/31/2016 | LS | A | Erie, PA |
| 0007450797 | WPTH906 | Extension of Second Deadline | 9/12/2016 | LS | A | Erie, PA |
| 0007438982 | WPTH907 | Extension of First Deadline | 8/31/2016 | LS | A | Traverse City, MI |
| 0007450798 | WPTH907 | Extension of Second Deadline | 9/12/2016 | LS | A | Traverse City, MI |
| 0007438983 | WPTH908 | Extension of First Deadline | 8/31/2016 | LS | A | Grand Rapids-Muskegon-Holland |
| 0007450799 | WPTH908 | Extension of Second Deadline | 9/12/2016 | LS | A | Grand Rapids-Muskegon-Holland |

**APPENDIX C**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **File Number** | **Call Sign** | **Purpose** | **Receipt Date** | **Radio Service Code** | **Channel Block** | **Market Name** |
| 0007441599 | WQHU548 | Extension of First Deadline | 9/2/2016 | LS | A  | Boston-Worcester-Lawrence-Lowe |
| 0007441600 | WQHU549 | Extension of First Deadline | 9/2/2016 | LS | A  | New York-No. New Jer.-Long Isl |
| 0007441601 | WQHU550 | Extension of First Deadline | 9/2/2016 | LS | A  | Philadelphia-Wilmington-Atl. C |
| 0007441602 | WQHU551 | Extension of First Deadline | 9/2/2016 | LS | A  | Washington-Baltimore, DC-MD-VA |
| 0007441603 | WQHU552 | Extension of First Deadline | 9/2/2016 | LS | A  | Richmond-Petersburg, VA |
| 0007441604 | WQHU553 | Extension of First Deadline | 9/2/2016 | LS | A  | Greensboro-Winston-Salem-High |
| 0007441605 | WQHU554 | Extension of First Deadline | 9/2/2016 | LS | A  | Raleigh-Durham-Chapel Hill, NC |
| 0007441606 | WQHU555 | Extension of First Deadline | 9/2/2016 | LS | A  | Charlotte-Gastonia-Rock Hill, |
| 0007441607 | WQHU556 | Extension of First Deadline | 9/2/2016 | LS | A  | Columbia, SC |
| 0007441608 | WQHU557 | Extension of First Deadline | 9/2/2016 | LS | A  | Savannah, GA-SC |
| 0007441609 | WQHU558 | Extension of First Deadline | 9/2/2016 | LS | A  | Jacksonville, FL-GA |
| 0007441610 | WQHU559 | Extension of First Deadline | 9/2/2016 | LS | A  | Orlando, FL |
| 0007441611 | WQHU560 | Extension of First Deadline | 9/2/2016 | LS | A  | Miami-Fort Lauderdale, FL |
| 0007441612 | WQHU561 | Extension of First Deadline | 9/2/2016 | LS | A  | Fort Myers-Cape Coral, FL |
| 0007441613 | WQHU562 | Extension of First Deadline | 9/2/2016 | LS | A  | Sarasota-Bradenton, FL |
| 0007441614 | WQHU563 | Extension of First Deadline | 9/2/2016 | LS | A  | Tallahassee, FL-GA |
| 0007441615 | WQHU564 | Extension of First Deadline | 9/2/2016 | LS | A  | Greenville-Spartanburg-Anderso |
| 0007441616 | WQHU565 | Extension of First Deadline | 9/2/2016 | LS | A  | Lexington, KY-TN-VA-WV |
| 0007441617 | WQHU566 | Extension of First Deadline | 9/2/2016 | LS | A  | Detroit-Ann Arbor-Flint, MI |
| 0007441618 | WQHU567 | Extension of First Deadline | 9/2/2016 | LS | A  | Milwaukee-Racine, WI |
| 0007441619 | WQHU568 | Extension of First Deadline | 9/2/2016 | LS | A  | Chicago-Gary-Kenosha, IL-IN-WI |
| 0007441620 | WQHU569 | Extension of First Deadline | 9/2/2016 | LS | A  | Nashville, TN-KY |
| 0007441621 | WQHU570 | Extension of First Deadline | 9/2/2016 | LS | A  | Memphis, TN-AR-MS-KY |
| 0007441622 | WQHU571 | Extension of First Deadline | 9/2/2016 | LS | A  | Jackson, MS-AL-LA |
| 0007441623 | WQHU572 | Extension of First Deadline | 9/2/2016 | LS | A  | Montgomery, AL |
| 0007441624 | WQHU573 | Extension of First Deadline | 9/2/2016 | LS | A  | Mobile, AL |
| 0007441625 | WQHU574 | Extension of First Deadline | 9/2/2016 | LS | A  | New Orleans, LA-MS |
| 0007441626 | WQHU575 | Extension of First Deadline | 9/2/2016 | LS | A  | Baton Rouge, LA-MS |
| 0007441627 | WQHU576 | Extension of First Deadline | 9/2/2016 | LS | A  | Little Rock-North Little Rock, |
| 0007441628 | WQHU577 | Extension of First Deadline | 9/2/2016 | LS | A  | Dallas-Fort Worth, TX-AR-OK |
| 0007441629 | WQHU578 | Extension of First Deadline | 9/2/2016 | LS | A  | Austin-San Marcos, TX |
| 0007441630 | WQHU579 | Extension of First Deadline | 9/2/2016 | LS | A  | Houston-Galveston-Brazoria, TX |
| 0007441631 | WQHU580 | Extension of First Deadline | 9/2/2016 | LS | A  | San Antonio, TX |
| 0007441632 | WQHU581 | Extension of First Deadline | 9/2/2016 | LS | A  | Casper, WY-ID-UT |
| 0007441633 | WQHU582 | Extension of First Deadline | 9/2/2016 | LS | A  | Denver-Boulder-Greeley, CO-KS- |
| 0007441634 | WQHU583 | Extension of First Deadline | 9/2/2016 | LS | A  | Spokane, WA-ID |
| 0007441635 | WQHU584 | Extension of First Deadline | 9/2/2016 | LS | A  | Idaho Falls, ID-WY |
| 0007441636 | WQHU585 | Extension of First Deadline | 9/2/2016 | LS | A  | Twin Falls, ID |
| 0007441637 | WQHU586 | Extension of First Deadline | 9/2/2016 | LS | A  | Boise City, ID-OR |
| 0007441638 | WQHU587 | Extension of First Deadline | 9/2/2016 | LS | A  | Reno, NV-CA |
| 0007441639 | WQHU588 | Extension of First Deadline | 9/2/2016 | LS | A  | Salt Lake City-Ogden, UT-ID |
| 0007441640 | WQHU589 | Extension of First Deadline | 9/2/2016 | LS | A  | Flagstaff, AZ-UT |
| 0007441641 | WQHU590 | Extension of First Deadline | 9/2/2016 | LS | A  | Albuquerque, NM-AZ |
| 0007441642 | WQHU591 | Extension of First Deadline | 9/2/2016 | LS | A  | Phoenix-Mesa, AZ-NM |
| 0007441643 | WQHU592 | Extension of First Deadline | 9/2/2016 | LS | A  | Tucson, AZ |
| 0007441644 | WQHU593 | Extension of First Deadline | 9/2/2016 | LS | A  | Los Angeles-Riverside-Orange C |
| 0007441645 | WQHU594 | Extension of First Deadline | 9/2/2016 | LS | A  | San Diego, CA |
| 0007441646 | WQHU595 | Extension of First Deadline | 9/2/2016 | LS | A  | Fresno, CA |
| 0007441647 | WQHU596 | Extension of First Deadline | 9/2/2016 | LS | A  | San Francisco-Oakland-San Jose |
| 0007441648 | WQHU597 | Extension of First Deadline | 9/2/2016 | LS | A  | Eugene-Springfield, OR-CA |
| 0007441649 | WQHU598 | Extension of First Deadline | 9/2/2016 | LS | A  | Portland-Salem, OR-WA |
| 0007441650 | WQHU599 | Extension of First Deadline | 9/2/2016 | LS | A  | Seattle-Tacoma-Bremerton, WA |
| 0007441651 | WQHU600 | Extension of First Deadline | 9/2/2016 | LS | A  | State College, PA |
| 0007441652 | WQHU601 | Extension of First Deadline | 9/2/2016 | LS | A  | Harrisburg-Lebanon-Carlisle, P |
| 0007441653 | WQHU602 | Extension of First Deadline | 9/2/2016 | LS | A  | Salisbury, MD-DE-VA |
| 0007441654 | WQHU603 | Extension of First Deadline | 9/2/2016 | LS | A  | Staunton, VA-WV |
| 0007441655 | WQHU604 | Extension of First Deadline | 9/2/2016 | LS | A  | Roanoke, VA-NC-WV |
| 0007441656 | WQHU605 | Extension of First Deadline | 9/2/2016 | LS | A  | Greenville, NC |
| 0007441657 | WQHU606 | Extension of First Deadline | 9/2/2016 | LS | A  | Augusta-Aiken, GA-SC |
| 0007441658 | WQHU607 | Extension of First Deadline | 9/2/2016 | LS | A  | Dothan, AL-FL-GA |
| 0007441659 | WQHU608 | Extension of First Deadline | 9/2/2016 | LS | A  | Albany, GA |
| 0007441660 | WQHU609 | Extension of First Deadline | 9/2/2016 | LS | A  | Macon, GA |
| 0007441661 | WQHU610 | Extension of First Deadline | 9/2/2016 | LS | A  | Columbus, GA-AL |
| 0007441662 | WQHU611 | Extension of First Deadline | 9/2/2016 | LS | A  | Chattanooga, TN-GA |
| 0007441663 | WQHU612 | Extension of First Deadline | 9/2/2016 | LS | A  | Knoxville, TN |
| 0007441664 | WQHU613 | Extension of First Deadline | 9/2/2016 | LS | A  | Pittsburgh, PA-WV |
| 0007441665 | WQHU614 | Extension of First Deadline | 9/2/2016 | LS | A  | Toledo, OH |
| 0007441666 | WQHU615 | Extension of First Deadline | 9/2/2016 | LS | A  | Fort Wayne, IN |
| 0007441667 | WQHU616 | Extension of First Deadline | 9/2/2016 | LS | A  | Champaign-Urbana, IL |
| 0007441668 | WQHU617 | Extension of First Deadline | 9/2/2016 | LS | A  | Evansville-Henderson, IN-KY-IL |
| 0007441669 | WQHU618 | Extension of First Deadline | 9/2/2016 | LS | A  | Paducah, KY-IL |
| 0007441670 | WQHU619 | Extension of First Deadline | 9/2/2016 | LS | A  | Greenville, MS |
| 0007441671 | WQHU620 | Extension of First Deadline | 9/2/2016 | LS | A  | Birmingham, AL |
| 0007441672 | WQHU621 | Extension of First Deadline | 9/2/2016 | LS | A  | Pensacola, FL |
| 0007441673 | WQHU622 | Extension of First Deadline | 9/2/2016 | LS | A  | Biloxi-Gulfport-Pascagoula, MS |
| 0007441674 | WQHU623 | Extension of First Deadline | 9/2/2016 | LS | A  | Shreveport-Bossier City, LA-AR |
| 0007441675 | WQHU624 | Extension of First Deadline | 9/2/2016 | LS | A  | Monroe, LA |
| 0007441676 | WQHU625 | Extension of First Deadline | 9/2/2016 | LS | A  | Fort Smith, AR-OK |
| 0007441677 | WQHU626 | Extension of First Deadline | 9/2/2016 | LS | A  | Fayetteville-Springdale-Rogers |
| 0007441678 | WQHU627 | Extension of First Deadline | 9/2/2016 | LS | A  | Springfield, MO |
| 0007441679 | WQHU628 | Extension of First Deadline | 9/2/2016 | LS | A  | Jonesboro, AR-MO |
| 0007441680 | WQHU629 | Extension of First Deadline | 9/2/2016 | LS | A  | Columbia, MO |
| 0007441681 | WQHU630 | Extension of First Deadline | 9/2/2016 | LS | A  | Peoria-Pekin, IL |
| 0007441682 | WQHU631 | Extension of First Deadline | 9/2/2016 | LS | A  | Davenport-Moline-Rock Island, |
| 0007441683 | WQHU632 | Extension of First Deadline | 9/2/2016 | LS | A  | Cedar Rapids, IA |
| 0007441684 | WQHU633 | Extension of First Deadline | 9/2/2016 | LS | A  | North Platte, NE-CO |
| 0007441685 | WQHU634 | Extension of First Deadline | 9/2/2016 | LS | A  | Abilene, TX |
| 0007441686 | WQHU635 | Extension of First Deadline | 9/2/2016 | LS | A  | San Angelo, TX |
| 0007441687 | WQHU636 | Extension of First Deadline | 9/2/2016 | LS | A  | Hobbs, NM-TX |
| 0007441688 | WQHU637 | Extension of First Deadline | 9/2/2016 | LS | A  | Lubbock, TX |
| 0007441689 | WQHU638 | Extension of First Deadline | 9/2/2016 | LS | A  | Amarillo, TX-NM |
| 0007441690 | WQHU639 | Extension of First Deadline | 9/2/2016 | LS | A  | Scottsbluff, NE-WY |
| 0007441691 | WQHU640 | Extension of First Deadline | 9/2/2016 | LS | A  | Honolulu, HI |
| 0007441692 | WQHU641 | Extension of First Deadline | 9/2/2016 | LS | A  | Puerto Rico & Virgin Isl. |
| 0007441693 | WQHU642 | Extension of First Deadline | 9/2/2016 | LS | A  | Gulf of Mexico |
| 0007441694 | WQHU643 | Extension of First Deadline | 9/2/2016 | LS | A  | Burlington, VT-NY |
| 0007441695 | WQHU644 | Extension of First Deadline | 9/2/2016 | LS | A  | Northern Michigan, MI |
| 0007441696 | WQHU645 | Extension of First Deadline | 9/2/2016 | LS | A  | Elkhart-Goshen, IN-MI |
| 0007441697 | WQHU646 | Extension of First Deadline | 9/2/2016 | LS | A  | Tupelo, MS-AL-TN |
| 0007441698 | WQHU647 | Extension of First Deadline | 9/2/2016 | LS | A  | Lafayette, LA |
| 0007441699 | WQHU648 | Extension of First Deadline | 9/2/2016 | LS | A  | Lake Charles, LA |
| 0007441700 | WQHU649 | Extension of First Deadline | 9/2/2016 | LS | A  | Joplin, MO-KS-OK |
| 0007441701 | WQHU650 | Extension of First Deadline | 9/2/2016 | LS | A  | Des Moines, IA-IL-MO |
| 0007441702 | WQHU651 | Extension of First Deadline | 9/2/2016 | LS | A  | Grand Forks, ND-MN |
| 0007441703 | WQHU652 | Extension of First Deadline | 9/2/2016 | LS | A  | Minot, ND |
| 0007441704 | WQHU653 | Extension of First Deadline | 9/2/2016 | LS | A  | Bismarck, ND-MT-SD |
| 0007441705 | WQHU654 | Extension of First Deadline | 9/2/2016 | LS | A  | Fargo-Moorhead, ND-MN |
| 0007441706 | WQHU655 | Extension of First Deadline | 9/2/2016 | LS | A  | Aberdeen, SD |
| 0007441707 | WQHU656 | Extension of First Deadline | 9/2/2016 | LS | A  | Rapid City, SD-MT-ND-NE |
| 0007441708 | WQHU657 | Extension of First Deadline | 9/2/2016 | LS | A  | Sioux Falls, SD-IA-MN-NE |
| 0007441709 | WQHU658 | Extension of First Deadline | 9/2/2016 | LS | A  | Sioux City, IA-NE-SD |
| 0007441710 | WQHU659 | Extension of First Deadline | 9/2/2016 | LS | A  | Omaha, NE-IA-MO |
| 0007441711 | WQHU660 | Extension of First Deadline | 9/2/2016 | LS | A  | Lincoln, NE |
| 0007441712 | WQHU661 | Extension of First Deadline | 9/2/2016 | LS | A  | Grand Island, NE |
| 0007441713 | WQHU662 | Extension of First Deadline | 9/2/2016 | LS | A  | Wichita, KS-OK |
| 0007441714 | WQHU663 | Extension of First Deadline | 9/2/2016 | LS | A  | Topeka, KS |
| 0007441715 | WQHU664 | Extension of First Deadline | 9/2/2016 | LS | A  | Tulsa, OK-KS |
| 0007441716 | WQHU665 | Extension of First Deadline | 9/2/2016 | LS | A  | Western Oklahoma, OK |
| 0007441717 | WQHU666 | Extension of First Deadline | 9/2/2016 | LS | A  | Santa Fe, NM |
| 0007441718 | WQHU667 | Extension of First Deadline | 9/2/2016 | LS | A  | Pueblo, CO-NM |
| 0007441719 | WQHU668 | Extension of First Deadline | 9/2/2016 | LS | A  | Billings, MT-WY |
| 0007441720 | WQHU669 | Extension of First Deadline | 9/2/2016 | LS | A  | Great Falls, MT |
| 0007441721 | WQHU670 | Extension of First Deadline | 9/2/2016 | LS | A  | Missoula, MT |
| 0007441722 | WQHU671 | Extension of First Deadline | 9/2/2016 | LS | A  | Farmington, NM-CO |
| 0007441723 | WQHU672 | Extension of First Deadline | 9/2/2016 | LS | A  | Redding, CA-OR |
| 0007441724 | WQHU673 | Extension of First Deadline | 9/2/2016 | LS | A  | Pendleton, OR-WA |
| 0007441725 | WQHU674 | Extension of First Deadline | 9/2/2016 | LS | A  | Richland-Kennewick-Pasco, WA |
| 0007441726 | WQHU675 | Extension of First Deadline | 9/2/2016 | LS | A  | Anchorage, AK |

**APPENDIX D**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **File Number** | **Call Sign** | **Purpose** | **Receipt Date** | **Radio Service Code** | **Channel Block** | **Market Name** |
| 0007441729 | WQGN602 | Extension of First Deadline | 9/2/2016 | LS | C | Sacramento-Yolo, CA |

1. Request for Extension of First Build-Out Date and Request for Waiver, filed August 29, 2016, and Request for Extension of Second Build-Out Date and Request for Waiver, filed September 12, 2016 (collectively, Wong-Armijo Extension and Waiver Requests). Appendix A to this *Public Notice* lists the related Universal Licensing System (ULS) file numbers and call signs. [↑](#footnote-ref-1)
2. 47 CFR § 90.155(d). The eighty-four Wong-Armijo licenses have midterm and final construction deadlines of September 4, 2016, and September 4, 2018, respectively. [↑](#footnote-ref-2)
3. FCR, Inc., Request for Waiver and For Extension of First Build-Out Deadline, filed August 31, 2016, and FCR, Inc., Request for Waiver and For Extension of Second Build-Out Deadline, filed September 12, 2016 (collectively, FCR Extension and Waiver Requests). Appendix B to this *Public Notice* lists the related ULS file numbers and call signs. [↑](#footnote-ref-3)
4. The thirteen FCR licenses have midterm and final construction deadlines of September 4, 2016, and September 4, 2018, respectively. [↑](#footnote-ref-4)
5. FCR’s licenses listed in Appendix B as WPOJ871 through WPOJ875 expire on July 14, 2019; WPTH901 through WPTH908 expire on October 5, 2021. [↑](#footnote-ref-5)
6. *See Arnold Leong v. Warren Havens et al.*, Case No. 2002-070640, Order Appointing Receiver After Hearing and Preliminary Injunction (Nov. 16, 2015).  The court appointed Susan L. Uecker as receiver (Receiver) to take control and possession of several entities, including Skybridge and Telesaurus, and the licenses held by those entities.  *Id.* at Attachment 1.  On December 17, 2015, the Receiver filed involuntary transfer of control applications on behalf of these entities seeking transfer of the licenses to Susan L. Uecker, Receiver; these applications were accepted in February 2016.  *See* ULS File Nos. 0007061847 and 0007060898 (filed Dec. 17, 2015). [↑](#footnote-ref-6)
7. Request for Extension of Time to Construct, filed September 2, 2016 (Skybridge/Telesaurus Extension Request). Appendices C and D to this *Public Notice* list the related ULS file numbers and call signs for Skybridge and Telesaurus, respectively. We refer to this request, the Wong-Armijo Extension and Waiver Requests, and the FCR Extension and Waiver Requests collectively as the Extension and Waiver Requests. [↑](#footnote-ref-7)
8. The 129 Skybridge/Telesaurus licenses have a midterm and final construction deadline of September 4, 2016, and September 4, 2018, respectively. [↑](#footnote-ref-8)
9. PCS Partners, L.P., Petition for Waiver of 47 CFR §90.353(b), and Request for Extension of Time and for Expedited Treatment filed April 15, 2016, and amended August 19, 2016 (PCS Partners’ Extension and Waiver Requests) (seeking a waiver of Section 90.353(b) of the Commission’s rules to permit machine type communications and requesting to extend its midterm and final construction requirements for thirty-one Channel Block A M-LMS licenses and one Channel Block C M-LMS license to 2020 and 2022, respectively). On May 4, 2016, the Bureau sought comment on PCS Partners’ Extension and Waiver Request. *See* *Wireless Telecommunications Bureau Seeks Comment on PCS Partners Requests for Multilateration Location and Monitoring Service Waiver and Construction Extension*, Public Notice, 31 FCC Rcd 4408 (WTB Mobility Div. 2016). The comment period ended on June 3, 2016, and PCS Partners’ applications and requests for relief remain pending. [↑](#footnote-ref-9)
10. *See* 47 CFR §§ 1.1200(a), 1.1206. [↑](#footnote-ref-10)